## Sheet1
Sprint 1
Task No | Task Name | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9
1 | Project Proposal | bar: Day 1
2 | Motion Sensor Logging | bar: Day 2
3 | Update Proposal from Critque | bar: Day 2 to Day 3
4 | Visualise Collected Data | bar: Day 3
5 | Code Solution | bar: Day 2 to Day 6
6 | Create Test Cases (Tweak Sensors) | bar: Day 5 to Day 6
7 | Train Sensors | bar: Day 5 to Day 6
8 | Test Initial Prototype | bar: Day 6 to Day 7
9 | Fix Critical Errors | bar: Day 6 to Day 7
10 | Demonstrate Initial Prototype | bar: Day 7 to Day 9
KEY
Completed
Remaining
Slack Time
t